## Detailed Road Map
Feature | Benefit to Product | Complexity | Risk | Priority | Version | Start Date | End Date | Duration
Market Research | Preform market research to gain insight into live music market | 3 | 5 | 1 |  | 2014-05-01 | 2014-05-07 | 6
1a. Define the Live Music market | Define how many users in the US go to live shows in a given year | 3 | 5 | 1 | Vo | 2014-05-01 | 2014-05-03 | 2
1b.. Users Interviews | Conduct interview with people who go to live shows to discover problems and pain points in going to live shows | 3 | 5 |  | Vo | 2014-05-01 | 2014-05-07 | 6
Define Product Hypothesis | Define what needs there are to people who go to live music | 3 | 5 | 1 |  | 2014-05-15 | 2014-05-17 | 2
1a. Define Product Hypothesis | Based on customer interviews, there appears to be a need for a way to tell users if they are going to like live show based on a yes or no answer | 2 | 2 | 1 | Vo | 2014-05-15 | 2014-05-17
MVP | This will expose risk and find if there is a product market for an active predictive engine | 2 | 1 | 1 | Vo | 2014-05-18 | 2014-05-31 | 13
1a. Build sms service | This allow the hypothesis of the product to be tested | 2 | 2 | 1 | Vo | 2014-05-18 | 2014-05-22 | 4
1b.Run Campaign | This will expose if there is a market for a service that predicts if a user will like a live show or not | 3 | 3 | 1 | Vo | 2014-05-23 | 2014-05-31 | 8
Recommendation Engine | Will provide the core feature of the application: to tell users if they are going to like a live concert or not | 1 | 1 | 1 | V1 | 2014-06-01 | 2014-12-31 | 213
1a. Develop the basic recommendation engine algorithm ( r.e.a) | Will provide the core feature of the application: to tell users if they are going to like a live concert or not | 1 | 1 | 1 | V1 | 2014-06-01 | 2014-12-31 | 213
1b. Integrate the user preferences into the r.e.a | The uses preferences will be added to r.e.a to personalize the experience and provide a more accurate results. | 2 | 2 | 1 | V1 | 2014-08-06 | 2014-08-09 | 3
Mobile Application | Platform on which users will interface with CoinFlip | 4 | 3 | 2 | V1 | 2014-06-01 | 2014-08-18 | 78
1.Applicatoin Framework | [5 empty] | 2014-06-01 | 2014-06-30 | 1900-01-28
1a. Design and build basic application frame working the Xamerine platform | This allow the basic framework of the application to be built in common language (C#) and than compiled for either the ios and or android platform. Allowing for maximum market coverage and saving on dev. Time and cost | 3 | 3 | 1 | V1 | 2014-06-01 | 2014-06-30 | 29
2.Login | [5 empty] | 2014-07-01 | 2014-07-10 | 1900-01-08
1a. Allow the user to user social media login to again access into the application | This will allow for a quick and easy onboarding process to new and returning users. This will also allow access to the users social media api data | 4 | 4 | 3 | V1 | 2014-07-01 | 2014-07-10 | 9
3. Account Setup Wizard | [5 empty] | 2014-07-11 | 2014-07-17 | 1900-01-05
3a. Set by the users preferences after login | This will combination of questions about location, price point, ect and logins to the users local media account. The inputs from this section will feed directly into the r.e.a., the more data the more accurate the results | 3 | 3 | 3 | V1 | 2014-07-11 | 2014-07-17 | 6
4.User Preferences | Data to feed into the recommendation engine |  |  |  |  | 2014-07-18 | 2014-08-05 | 1900-01-17
4a. Integrate list of artists from the users local device | The artists, genre, and the number of plays are factored into the recommendation engine to get a better prediction if a user will like a show or not | 4 | 4 | 2 | V1 | 2014-07-18 | 2014-07-20 | 2
4b. Integrate with the Facebook API to get a list of liked Bands | The artist and genre are added into the recommendation engine to get a better prediction if a user will like a like show or not | 4 | 4 | 2 | V1 | 2014-07-21 | 2014-07-22 | 1
4c. Integrate with music social APIs ( Pandora, Spottily, Google Play, ect) | The artist and genre are added into the recommendation engine to get a better prediction if a user will like a like show or not | 4 | 4 | 2 | V1 | 2014-07-23 | 2014-07-25 | 2
4d.Intergrate with the Facebook API see which friends are going to which shows and when | The number of friends that are going to a show and if they liked the band's FB page are data to be fed into the recommendation engine | 4 | 4 | 2 | V1 | 2014-07-28 | 2014-07-30 | 2
4e. Price Point | Build a system in which the user can set the maximum dollar value that they will pay for a live show. | 5 | 5 | 2 | V1 | 2014-07-31 | 2014-08-01 | 1
4f. Location | This will tell the application where the users and based on geographic tolerances will provide data for the r.e.a | 4 | 4 | 2 | V1 | 2014-08-03 | 2014-08-05 | 2
5.Home Screen | [5 empty] | 2014-07-01 | 2014-07-15 | 1900-01-13
5a. List what trending for the user based on the user preferences | This will allow users a quick and simple dashboard view of their : Music likes, friends activity, concerts near you, news about your favorite bands | 3 | 3 | 3 | V1 | 2014-07-01 | 2014-07-06 | 5
5b. Integrate with music news feed | This will provide news about artists that they user likes based on their social media provide. This also provide incentive for the user to return to the application and get excited about asking the app if they will like a show or not. | 3 | 2 | 3 | V1 | 2014-07-09 | 2014-07-15 | 6
6.Reconiindation Screen | [5 empty] | 2014-07-16 | 2014-07-21 | 2014-06-30
6a. Provide a search input screen such that users can enter the live shows that want a recommendation for | Users will be receive a yes or no answer to the question if they will enjoy going to a live show or not based on r.e.a.. The user will than to be taken though a purchase flow to buy tickets to the show. | 4 | 3 | 2 | V1 | 2014-07-16 | 2014-07-18 | 2
6b. Provide a list of trending shows based on the users preferences | This is provide a passive list of shows in the users areas to keep the users up to date on live shows in their areas and to spark their interest in going to live shows. | 4 | 4 | 4 | V1 | 2014-07-19 | 2014-07-21 | 2
7.Buy API Integration | Will allow the users to directly buy concert tickets from the app |  |  |  |  | 2014-07-22 | 2014-07-25 | 3
7a. Integrate the purchase API with the application | This will allow the users to purchase tickets to the live show after the active recommendation engine gives them a positive result | 3 | 3 | 5 | V2 | 2014-07-22 | 2014-07-25 | 3
8.Calendar Screen | Will allow the user to add shows to their personal calendars |  |  |  |  | 2014-07-26 | 2014-07-28 | 2
8a. Integrate the application with the users device calendar | This will allow the user add concerts to their calendar so that they can keep track of up coming shows | 4 | 5 | 2 | V1 | 2014-07-26 | 2014-07-28 | 2
9.Push Notifications | Will remind the user that a show happening and ask them if they are there or not. |  |  |  |  | 2014-07-29 | 2014-08-12 | 14
9a. Add support for Push Notifications for when a show is about to start | This will allow users to receive a notification that a show is about to start and will add a verication loop that users attended the show | 4 | 5 | 2 | V1 | 2014-07-29 | 2014-08-03 | 5
9b. Add support for Push Notifications with a deep to directions to the show | This will allows easy access to directions to the show | 4 | 4 | 3 | V1 | 2014-08-04 | 2014-08-06 | 2
9c. Push Notifications to alert users of upcoming shows of their favorite bands | This will allow for quick access to to tour information on their favorite band and create an insentive to use the app | 4 | 4 | 3 | V1 | 2014-08-07 | 2014-08-09 | 2
9d. Push Notifications to alert users of news articles and concert reviews of their favorite bands | This allow quick access to news articles and blogs on their favorite bands and create insentive to use the app | 4 | 3 | 3 | V1 | 2014-08-10 | 2014-08-12 | 2
10.User Logging | Each Key user interaction will be logged and stored on the server |  |  |  |  | 2014-06-15 | 2014-07-03 | 18
10a. Integrate user logging in the application | Each user interaction with the application will be stored on user bases to track how the users make decisions on which live concerts that will go to | 3 | 3 | 2 | V1 | 2014-06-15 | 2014-07-01 | 16
10b. Store the log reports on the server | Each users analytic data will be stored on the server's back end | 3 | 3 | 2 | V1 | 2014-07-02 | 2014-07-03 | 1
11.User Referal | Allow users to refer other users to use Coin Flip | [6 empty] | 5
11a.: Add functionality to invite other users to use the application | This will create another discovory channel for CoinFlip | 3 | 3 | 2 | V1 | 2014-08-13 | 2014-08-18 | 5
11b. Add functionality to promote activity on the app to social media to build brand awareness | This will create another discovory channel for CoinFlip | 3 | 3 | 2 | V1 | 2014-08-13 | 2014-08-18 | 5
Server | Provide Data for the application to interact with | 3 | 3 | 2 | V1 | 2014-06-01 | 2014-08-01 | 61
1.Front Server | Provide the online platform in which the application will interact with |  |  |  |  | 2014-06-01 | 2014-08-01 | 61
1a. Build a front end server | Provide the online platform in which the application will interact with | 2 | 2 | 1 | V1 | 2014-06-01 | 2014-08-15 | 75
2.Back End Server | Provide the online platform in which the application will interact with |  |  |  |  | 2014-06-15 | 2014-08-01 | 47
2a. Build a back end data base | Provide a back end data base to store the user records and data | 3 | 3 | 1 | V1 | 2014-06-15 | 2014-08-01 | 47
Reporting | [5 empty] | 2014-08-01 | 2015-08-04 | 156
1.User Reports | Provide the end user data reports
1a. Set up automated scripts to pull and format end user data into reports | Historical reports can be generated automatically without human input | 3 | 3 | 2 | V1 | 2014-08-01 | 2014-08-05 | 4
1b. Publish Reports | These reports will be sold to interested parties | 3 | 3 | 2 | V1 | 2015-01-03 | 2015-01-04 | 1
Pre-Launch Marketing | Rise the awareness of the Coionflip application prior to launch | 2 | 2 | 2 | V1 | 2014-10-01 | 2014-12-31 | 91
1a. Social Media Marketing Campaigns |  | 2 | 3 | 2 | V1 | 2014-10-01 | 2014-12-31
1b. Online Marketing Campaigns |  | 2 | 2 | 2 | V1 | 2014-10-01 | 2014-12-31
Application Launch | Make the applicattion aviable to download on the Mobile store fronts |  |  |  |  | 2015-01-03 | 2015-01-04 | 1
1a.Pubublish to Itunes |  | 5 | 5 | 1 | V1 | 2015-01-03 | 2015-01-04 | 1
1b.Publish to Google Play |  | 5 | 5 | 1 | V1 | 2015-01-03 | 2015-01-04 | 1
Post- Launch Marketing: Growth | Drive users to download page on the mobile store fronts | 2 | 2 | 1 | V1 | 2015-01-03 | 2015-03-01 | 57
Application Dev: Refindment and market Growth | Feature revindment to ensure users get the most out of the application |  |  |  |  | 2015-01-04 | 2015-02-28 | 55
1a. Review User interaction logs | To see how the users are interacting with the applicatoin | 1 | 3 | 2 | V2 | 2015-01-04 | 2015-01-31 | 27
1b. Remove feaetures that not being used | Remove application features so that the users can focus on key areas of the application | 1 | 3 | 2 | V2 | 2015-01-14 | 2015-02-14 | 31
1c. Refind current features in the application | Refind curent features application features so that the users can use the application more effiantly | 1 | 2 | 1 | V2 | 2015-01-14 | 2015-02-14 | 31
1d. Add product features | Add targeted prouct features designed to grow usesage | 2 | 2 | 3 | V2 | 2015-01-14 | 2015-02-14 | 31
1e. Run A to B tests on application designs | To ensure that changes to application will drive useage and grow market share | 2 | 2 | 1 | V2 | 2015-02-15 | 2015-02-28 | 13
Launch V2 of the Application | [5 empty] | 2015-03-01 | 2015-03-02 | 1
1a. Push new version of the applicaiotn to mobile store fronts | Push new version of the applicatino designed to grow market share and increase useage | 3 | 3 | 1 | V2 | 3/1/15/ | 2015-03-02
Revenue Growth | Grow Revenue |  |  |  |  | 2015-03-01 | 2015-07-31 | 152
1a. Buniess Dev. Efforts to grow Renenue | Find new consumers of the user data and grow the revenue | 1 | 1 | 1 | V2 | 2015-03-01 | 2015-07-31 | 152
User Retention and market Growth |  | 2 | 2 | 1 |  | 2015-03-01 | 2015-07-31 | 152
1a. Marketing Campaigns | To remind the users the value of CoinFlip | 1 | 2 | 1 | v3 | 2015-03-01 | 2015-04-30 | 60
1b. Contests | To reminds the users of the value of CoinFlip and drive new users to the applicaton | 1 | 3 | 1 | v3 | 2015-05-01 | 2015-07-31 | 91
Formulas:
Start Date = [Start Date, row below]
Start Date = [Start Date, row above]
End Date = [End Date, row above]
End Date = [End Date, row below]

## Road Map
Feature | Benefit to Product | Complexity | Risk | Priority | Version | Start Date | End Date | Duration
Market Research | Preform market research to gain insight into live music market | 3 | 5 | 1 | Vo | 2014-05-01 | 2014-05-07 | 6
Define Product Hypothesis | Define what needs there are to people who go to live music | 3 | 5 | 1 | Vo | 2014-05-15 | 2014-05-17 | 2
MVP | This will expose risk and find if there is a product market for an active predictive engine | 2 | 1 | 1 | Vo | 2014-05-18 | 2014-05-31 | 13
Mobile Application | Platform on which users will interface with CoinFlip | 4 | 3 | 2 | V1 | 2014-06-01 | 2014-08-18 | 78
Server | Provide Data for the application to interact with | 3 | 3 | 2 | V1 | 2014-06-01 | 2014-08-01 | 61
Reporting Dev. | Historical reports can be generated automatically without human input | 3 | 3 | 2 | V1 | 2014-08-01 | 2014-08-05 | 4
Recommendation Engine | Will provide the core feature of the application: to tell users if they are going to like a live concert or not | 1 | 1 | 1 | V1 | 2014-06-01 | 2014-12-31 | 213
Pre-Launch Marketing | Rise the awareness of the CoinFlip application prior to launch | 2 | 2 | 2 | V1 | 2014-10-01 | 2014-12-31 | 91
Reporting Publish Reports | These reports will be sold to interested parties | 3 | 3 | 2 | V1 | 2015-01-03 | 2015-01-04 | 1
Application Launch | Make the application for download on the Mobile store fronts | 5 | 5 | 1 | V1 | 2015-01-03 | 2015-01-04 | 1
Post- Launch Marketing: Growth | Drive users to download page on the mobile store fronts | 2 | 2 | 1 | V1 | 2015-01-03 | 2015-03-01 | 57
Application Dev: Refinement and market Growth | Feature refinement to ensure users get the most out of the application | 2 | 2 | 1 | V2 | 2015-01-04 | 2015-02-28 | 55
Launch v2 of the Application | Push updates to the application aimed at growth | 4 | 4 | 1 | V2 | 2015-03-01 | 2015-03-02 | 1
Feature Retention and market Growth | Grow Market Share | 2 | 2 | 1 | V2 | 2015-03-01 | 2015-07-31 | 152
Revenue Growth | Grow Revenue | 2 | 2 | 1 | V3 | 2015-04-20 | 2015-12-31 | 255